## Summary
Project ID |  |  |  |  | Planned Start | 2022-03-14 |  |  | Estimated Effort (Hr) |  | Testing Type | Internal Testing |  | STATUS
Project Name |  |  |  |  | Planned End | 2022-03-23 |  |  |  |  | Testing Method | Manual | Manual (Onsite)
Project Manager/Lead |  | Surender Kajla |  |  | Actual Start | 2022-03-14 |  |  | Actual Effort (Hr) |  | TEST Data Status
Project PIC | Sourabh |  |  |  | Actual End | 2022-03-24 |  |  |  |  | Test Round
Test Manager |  |  |  |  | TCN |  |  |  | Defect Density |  | Sonar Status(Quality)
Test PIC | Sourabh |  |  |  | TCN Pass (%) | [5 empty] | Line of Codes
Testing Round |  | Actual |  |  | Test Cases | TCN Status
Sno | Tester | Start Date | End Date | Effort(Hrs) | No of Test Case Notes | Pass | Fail | Not Run | Blocker | Pass with Exception | Testing Confirmed By | Testing Status |  | Scope
1 | Harshul | 2022-03-14 | 2022-03-23 |  | 66 | 71 | 7 | 0 | 0 | 0
2 | Harshul | 2022-03-23 | 2022-03-24 |  | 71 | 71 | 0 | 0 | 0 | 0

## Test Cases >>
Testing Round Summary

## Test cases
Sr No | Use Case Id | Type | Priority | Test Case | Verification Method | Expected Results | Test Data | Round 1 Status | Bug Id | Round 2 Status | Bug Id | Round 3 Status | Bug Id
| UC-001: Login | User Interface | Low | Check if login screen layout is proper | Visual | Screen layout should be proper |  | Pass |  | Pass
| UC-001: Login | User Interface | Low | Check if fonts type, size, color are proper | Visual | Fonts type, size, color should be proper |  | Pass |  | Pass
| UC-001: Login | Functional | High | Check if the Login URL is executable or not | Test Data | Login Screen will open. |  | Pass |  | Pass
| UC-001: Login | Functional | High | Chek if the fields to enter the username and password is present on the screen and are editable. | Event - Click | The field to enter the username and password should be present and it should accept input. |  | Pass |  | Pass
| UC-001: Login | Functional | High | Check if the submit button is present and is clickable. | Event - Click | The submit button should be clickable. |  | Pass |  | Pass
| UC-001: Login | Functional | High | Check if the user is able to login to the application with the incorrect username and password . | Test Data | User should not be able to login to the application and error message should be displayed. |  | Pass |  | Pass
| UC-001: Login | Functional | High | Check if the user is able to login to the application if the username is correct and password is incorrect. | Test Data | User should not be able to login to the application and error message should be displayed. |  | Pass |  | Pass
| UC-001: Login | Functional | High | Check if the user is able to login to the application if the username and password is correct. | Test Data | User should be able to login to the Home page . |  | Pass |  | Pass
| UC-001: Login | Validation | Medium | Check if the user is able to login to the application if the password is less then 4 character | Test Data | User should not be able to login to the Home page, if the password is less then 4 character. |  | Pass |  | Pass
| UC-001: Login | Validation | Medium | Check if the user is able to login to the application if the password is more then then 12 character | Test Data | User should not be able to login to the Home page, if the password is more then 12 character. |  | Pass |  | Pass
| UC-001: Login | Validation | Medium | Check if the user is able to login to the application keeping username field empty. | Test Data | User should not be able to login to the application keeping username field empty. |  | Pass |  | Pass
| UC-002:Logout | User Interface | Medium | check if the Logout button is present on the navbar. | Visual | Logout button should be present. |  | Pass |  | Pass
| UC-002:Logout | Functional | High | Check if the Logout button is clickable or not. | Event - Click | Logout button should be clickable. |  | Pass |  | Pass
| UC-002:Logout | Functional | High | Check whether the user has successfully logged out after clicking on the logout button and login screen should appear. | Event - Click | User should be logout after clicking on the logout button and login screen appears. |  | Pass |  | Pass
| UC-003: Home page | User Interface | Low | Check if home screen layout is proper | Visual | Screen layout should be proper |  | Pass |  | Pass
| UC-003: Home page | User Interface | Low | Check if fonts type, size, color are proper | Visual | Fonts type, size, color should be proper |  | Pass |  | Pass
| UC-003: Home page | User Interface | Low | Check whether the navigation bar is available. | Visual | The navigation bar should be avilable |  | Pass |  | Pass
| UC-003: Home page | User Interface | Medium | Check whether following options are being displayed on the screen : (a) Home (b) Create Project (c) Search Button (d)LogOut | Visual | All the option should be available on the screen. |  | Pass |  | Pass
| UC-003: Home page | Functional | Medium | Check if the Home button is present and is clickable. | Event - Click | The Home button should be clickable and redirect to only Home page not on any other page. |  | Pass |  | Pass
| UC-003: Home page | Functional | High | Check if the Create Project button is present and is clickable. | Event - Click | The Create Project button should be present and clickable. |  | Pass |  | Pass
| UC-003: Home page | Functional | High | Check if the Search button is present and is clickable. | Event - Click | The Search button should be present and clickable. |  | Pass |  | Pass
| UC-003: Home page | Functional | Medium | Check if the logout button is present and clickable . | Event - Click | Log out button should be present and clickable. |  | Pass |  | Pass
| UC-003: Home page | Functional | Medium | Check if the Update Project Button is present and is clickable for all the updatable projects | Event - Click | The Update Project button should be present and clickable for all the updatable projects. |  | Pass |  | Pass
| UC-003: Home page | Functional | Medium | Check if the Delete Project button is present and is clickable for the projects that can be deleted | Event - Click | The Delete Project button should be present and clickable for the projects that can be deleted. |  | Pass |  | Pass
| UC-004:Create Project | Functional | High | Check if Create Project screen appears on clicking create project button. | Event - Click | Create Project screen should open. |  | Pass |  | Pass
| UC-004:Create Project | User Interface | Low | Check layout of create project screen | Visual | Create Project screen layout should be proper |  | Pass |  | Pass
| UC-004:Create Project | User Interface | Low | Check if fonts type, size, color are proper | Visual | Fonts type, size, color should be proper |  | Pass |  | Pass
| UC-004:Create Project | Functional | High | Check if user is able to enter all the details to Create the Project. | Event - Click | User should be able to enter all the details to Create the Project. |  | Pass |  | Pass
| UC-004:Create Project | Validation | Medium | Cheack if the user is able to create project keeping any of the mandatory fields empty. | Event - Click | User should not be able to create project keeping any of the mandatory field empty. |  | Pass |  | Pass
| UC-004:Create Project | Functional | High | Check if the Submit button is present and clickable | Event - Click | On Clicking project should be created and added to list. |  | Pass |  | Pass
| UC-004:Create Project | Functional | Medium | Check if the success message is being displayed | Visual | Success message should be displayed after creating project. |  | Pass |  | Pass
| UC-004:Create Project | Validation | High | Check if the user is able to create project having end date less then start date | Test Data | User should not be able to create project having end date less then start date |  | Pass |  | Pass
| UC-004:Create Project | Functional | High | Check if not authorised user can go to the create project screen using URL directly | Event - Click | Not authorised user should not be able to go to the create project screen using URL directly |  | Fail | 1 | Pass
| UC-004:Create Project | Validation | Medium | Check if user is able to create project by giving less then 2 character in the project name and Client Name Field. | Test Data | User should not be able to create project by giving less then 2 character in the project name and Client Name Field. |  | Pass |  | Pass
| UC-004:Create Project | Validation | Medium | Check if user is able to create project by giving more then 50 character in the project name and Client Name Field. | Test Data | User should not be able to create project by giving more then 50 character in the project name and Client Name Field. |  | Pass |  | Pass
| UC-004:Create Project | Validation | Medium | Check if user is able to create project giving only spaces in Project Name and Client Name fields. | Test Data | User should not be able to create project giving only spaces in Project Name and Client Name fields. |  | Fail | 2 | Pass
| UC-005:Update Project | User Interface | Medium | Check whether the Update button is present on all the projects. | Visual | Update button should be present. |  | Pass |  | Pass
| UC-005:Update Project | Functional | Medium | Check whether the Update Project button is clickable for the projects with status 'Not Started' ,'In Progress'. | Event - Click | Update Project button should be clickable for the projects with status 'Not Started' and 'In Progress'. |  | Pass |  | Pass
| UC-005:Update Project | Functional | High | Check whether the Update Project button is clickable for the projects with status 'Completed'. | Event - Click | Update Project button should not be clickable for the projects with status 'Completed'. |  | Pass |  | Pass
| UC-005:Update Project | Functional | High | Check if on clicking Update Button, Update Project screen is opening. | Event - Click | On clicking Update Button, Update Project screen should open. |  | Pass |  | Pass
| UC-005:Update Project | User Interface | Low | Check Update Project screen layout. | Visual | Update Project screen layout should be proper. |  | Pass |  | Pass
| UC-005:Update Project | User Interface | Low | Check if fonts type, size, color are proper | Visual | Fonts type, size, color should be proper |  | Pass |  | Pass
| UC-005:Update Project | Functional | Medium | Check weather the Update Details form is pre-filled. | Visual | Update Details form sholud be pre-filled. |  | Pass |  | Pass
| UC-005:Update Project | Functional | High | Check weather user is able to enter all the details to Update the Project. | Event - Click | User should be able to enter all the details to Update the Project. |  | Pass |  | Pass
| UC-005:Update Project | Functional | High | Check weather the Submit button is present and clickable | Event - Click | On clicking project should be updated. |  | Pass |  | Pass
| UC-005:Update Project | Functional | High | Check if not authorised user can go to the Update project screen using URL directly | Event - Click | Not authorised user should not be able to go to the update project screen using URL directly |  | Fail | 3 | Pass
| UC-005:Update Project | Functional | High | Check if not updatable project can be deleted using URL directly | Event - Click | Not updatable project should not be deleted using URL directly |  | Fail | 4 | Pass
| UC-005:Update Project | Validation | Medium | Check if user is able to update project by giving less then 2 character in the project name and Client Name Field. | Test Data | User should not be able to update project by giving less then 2 character in the project name and Client Name Field. |  | Pass |  | Pass
| UC-005:Update Project | Validation | Medium | Check if user is able to update project by giving more then 50 character in the project name and Client Name Field. | Test Data | User should not be able to update project by giving more then 50 character in the project name and Client Name Field. |  | Pass |  | Pass
| UC-005:Update Project | Validation | Medium | Check if user is able to update project giving only spaces in Project Name and Client Name fields. | Test Data | User should not be able to update project giving only spaces in Project Name and Client Name fields. |  | Fail | 5 | Pass
| UC-006:Delete Project | User Interface | Medium | Check whether the Delete button is present on all the projects | Visual | Delete button should be present. |  | Pass |  | Pass
| UC-006:Delete Project | Functional | High | Check whether the Delete button is clickable on projects with status - 'Completed' and 'In Progress' | Event - Click | Delete button should be disabled on projects with status - 'Completed' and 'In Progress'. |  | Pass |  | Pass
| UC-006:Delete Project | Functional | High | Check whether delete button is clickable for the projects with status - 'Not Started' | Event - Click | Delete button should be clickable for the projects with status - 'Not Started' |  | Pass |  | Pass
| UC-006:Delete Project | Functional | Medium | Check weather confirmation Modal Box appears on clicking Delete Button | Event - Click | Confirmation Modal Box appears on clicking Delete Button. |  | Pass |  | Pass
| UC-006:Delete Project | User Interface | Low | Check the layout of Modal box | Visual | Modal box layout should be proper. |  | Pass |  | Pass
| UC-006:Delete Project | User Interface | Medium | Check whether Cancel button and 'Yes' button is present. | Visual | Cancel button and 'Yes' button should be present. |  | Pass |  | Pass
| UC-006:Delete Project | Functional | Medium | Check whether on clicking Cancel button, it takes to home page | Visual | On clicking Cancel button, it should take to home page |  | Pass |  | Pass
| UC-006:Delete Project | Functional | High | Check whether on clicking 'Yes' button, it deletes the project | Visual | On clicking 'Yes' button, it should delete the project. |  | Pass |  | Pass
| UC-006:Delete Project | Functional | Medium | Check weather success message is being displayed after deleting. | Visual | Success message should be displayed after deleting. |  | Pass |  | Pass
| UC-006:Delete Project | Functional | High | Check if not authorised user can delete the project using URL directly | Event - Click | Not authorised user should not be able to delete the project using URL directly |  | Fail | 6 | Pass
| UC-006:Delete Project | Functional | High | Check if not deletable project can be deleted using URL directly | Event - Click | Not deletable project can not be deleted using URL directly |  | Fail | 7 | Pass
| UC-007:Search Project | User Interface | High | Check if the search button is present and clickable. | Event - Click | Search Button should be present and clickable |  | Pass |  | Pass
| UC-007:Search Project | Functional | High | Check if the search field is accepting input from the user | Event - Click | Search field should accept the name of the project to be searched. |  | Pass |  | Pass
| UC-007:Search Project | Functional | High | On clicking search button, check whether the project being searched is displayed | Event - Click | On clicking search button, project being searched should be displayed on the screen. |  | Pass |  | Pass
| UC-007:Search Project | Validation | Medium | Check if user is able to search for the project irrespective of letter case | Event - Click | User should be able to search for the project irrespective of letter case. |  | Pass |  | Pass
| UC-007:Search Project | Functional | High | Check if user is able to search for the project using project name | Event - Click | User should be able to search for the project using project name |  | Pass |  | Pass
| UC-007:Search Project | Functional | High | Check if user is able to search for the project using client name | Event - Click | User should be able to search for the project using client name |  | Pass |  | Pass
| UC-008:Show Project Details | Functional | Medium | On clicking project name, check whether modal box appears or not. | Event - Click | On clicking project name, modal box should appear showing all the project details. |  | Pass |  | Pass
| UC-008:Show Project Details | User Interface | Low | Check if Modal Box layout is proper. | Visual | Modal Box layout should be proper. |  | Pass |  | Pass
| UC-008:Show Project Details | User Interface | Low | Check if fonts type, size, color are proper | Visual | Fonts type, size, color should be proper. |  | Pass |  | Pass
| UC-008:Show Project Details | Functional | High | Check weather Modal Box is showing all the details | Visual | Modal Box should show all the details related to the project. |  | Pass |  | Pass
| UC-008:Show Project Details | User Interface | Medium | Check weather the close button is present and clickable | Event - Click | Close button should be present and clickable |  | Pass |  | Pass
| UC-008:Show Project Details | Functional | High | On clicking close button, check weather it is taking to home page. | Event - Click | On clicking close button, check weather it is taking to home page. |  | Pass |  | Pass

## BUGS >>
BUGS Status
Sum of Bug ID | Column Labels
Row Labels | (blank) | Grand Total
(blank)
Grand Total

## Bugs
Bug ID | Bug Description | Test Result | Type of Issue | Status | Assign To | Developer Comment | Tester Comments
1 | Not authorised user is able to go to the create project screen using URL directly |  | Functionality | Closed
2 | If User gives only spaces in Username field, then app is accepting this type of input |  | Functionality | Closed
3 | Not authorised user is able to go to the update project screen using URL directly |  | Functionality | Closed
4 | Not updatable project could be deleted using URL directly |  | Functionality | Closed
5 | User should is able to update project giving only spaces in Project Name and Client Name fields. |  | Functionality | Closed
6 | Not authorised used should not be able to delete project URL directly |  | Functionality | Closed
7 | Not deletable project could be deleted using URL directly |  | Functionality | Closed

## Test Data >>
Test Data
Prepared By | Updated On | Verified By | Verified On